## Gantt chart
Month | October | Novemember |  |  |  | December |  |  |  |  | January |  |  |  | Febuary |  |  |  | March |  |  |  | Apri
Official week num | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Week num (W/C) | 5 (29th) | 1 (5th) | 2 (12th) | 3 (19th) | 4 (26th) | 1 (3rd) | 2 (10th) | 3 (17th) | 4 (24th) | 5 (31st) | 1 (7th) | 2 (14th) | 3 (21st) | 4 (28th) | 1 (4th) | 2 (11th) | 3 (18th) | 4 (25th) | 1 (4th) | 2 (11th) | 3 (18th) | 4 (25th) | 1 (1st) | 2 (8th) | 3 (15th) | 4 (22nd) | 5 (29th)
Research | December 12: No work for christmas; Apri 31: Deadline
Design | bar: Novemember 7 to December 10; December 12 to December 13; Apri 31
Implementation | bar: December 12 to March 25; Apri 31
Containgency | bar: December 11 to December 13; March 26 to Apri 31
[8 empty] | Holiday |  |  | Revise | Exams
Ness submissions | Novemember 9: Dragons den - 28th; December 10: Peer review 1 - 7th; December 11: Draft spec & test plan - 12th; Febuary 22: Design diagrams and UI designs - 28th; March 23: Final requirements and test plan - 8th; March 26: Poster for trade fair - 29th; Apri 31: Peer review 2 - 3rd

## Details for each
Research | Look into other apps
Meet client
Gather info about building (floor plan etc.)
Research user heiristics
Android development techniques
Google maps API
Open souce andriod frameworks
Images of building (which we need)
Web design needs
Design | App layout design (UI)
Specification
Web design
Plan implementation
Implementation | This will be updated once specification is drawn up