## Gantt chart
Month | October | Novemember |  |  |  | December |  |  |  |  | January |  |  |  | Febuary |  |  |  | March |  |  |  | Apri
Week (W/C) | 5 (29th) | 1 (5th) | 2 (12th) | 3 (19th) | 4 (26th) | 1 (3rd) | 2 (10th) | 3 (17th) | 4 (24th) | 5 (31st) | 1 (7th) | 2 (14th) | 3 (21st) | 4 (28th) | 1 (4th) | 2 (11th) | 3 (18th) | 4 (25th) | 1 (4th) | 2 (11th) | 3 (18th) | 4 (25th) | 1 (1st) | 2 (8th) | 3 (15th) | 4 (22nd) | 5 (29th)
Research | [7 empty] | No work for christmas | [18 empty] | Deadline
Design
Implementation
Containgency
[8 empty] | Holiday |  |  | Revise | Exams
Ness submissions |  |  |  |  | Dragons den - 28th | Peer review 1 - 7th | Draft spec & test plan - 12th | [10 empty] | Design diagrams and UI designs - 28th | Final requirements and test plan - 8th |  |  | Poster for trade fair - 29th |  |  |  |  | Peer review 2 - 3rd

## Details for each
Research | Look into other apps
Meet client
Gather info about building (floor plan etc.)
Research user heiristics
Android development techniques
Google maps API
Open souce andriod frameworks
Images of building (which we need)
Web design needs
Design | App layout design (UI)
Specification
Web design
Plan implementation
Implementation | This will be updated once specification is drawn up