## Gantt chart
Month | October | Novemember |  |  |  | December |  |  |  |  | January |  |  |  | Febuary |  |  |  | March |  |  |  | Apri
Official week num | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
Week num (W/C) | 5 (29th) | 1 (5th) | 2 (12th) | 3 (19th) | 4 (26th) | 1 (3rd) | 2 (10th) | 3 (17th) | 4 (24th) | 5 (31st) | 1 (7th) | 2 (14th) | 3 (21st) | 4 (28th) | 1 (4th) | 2 (11th) | 3 (18th) | 4 (25th) | 1 (4th) | 2 (11th) | 3 (18th) | 4 (25th) | 1 (1st) | 2 (8th) | 3 (15th) | 4 (22nd) | 5 (29th)
Research | December 12 3 (17th): No work for christmas; Apri 31 5 (29th): Deadline
Design | bar: Novemember 7 2 (12th) to December 10 1 (3rd); December 12 3 (17th) to December 13 4 (24th); Apri 31 5 (29th)
Implementation | bar: December 12 3 (17th) to December 13 4 (24th); January 18 4 (28th) to March 25 3 (18th); Apri 31 5 (29th)
Containgency | bar: December 11 2 (10th) to December 13 4 (24th); March 26 4 (25th) to Apri 31 5 (29th)
[8 empty] | Holiday |  |  | Revise | Exams
Ness submissions | Novemember 9 4 (26th): Dragons den - 28th; December 10 1 (3rd): Peer review 1 - 7th; December 11 2 (10th): Draft spec & test plan - 12th; Febuary 22 4 (25th): Design diagrams and UI designs; March 23 1 (4th): Final requirements and test plan - 8th; March 26 4 (25th): Poster for trade fair - 29th; Apri 31 5 (29th): Peer review 2 - 3rd
feedback only
In thurs meeting
Non submission milestones | Novemember 8 3 (19th): Basic prototype to show layout of app; January 18 4 (28th): List of: pages, classes, major methods; Febuary 21 3 (18th): Front end soft - drawn plans into NF pages; March 23 1 (4th): Website soft; March 25 3 (18th): Back end soft
|  |  |  | Website mockup drawn | [16 empty] | Trade fair poster soft

## Details for each
Research | Look into other apps | Done
| Meet client | Done
| Gather info about building (floor plan etc.) | Done
| Research user heiristics | Done
| Android development techniques | Done
| Google maps API | Done
| Open souce andriod frameworks | Done
| Images of building (which we need) | Ongoing
| Web design needs | Done
Design | App layout design (UI) Storyboard | Done
| Specification (requirements & criteria) | Done
| Web design | Done
| Plan implementation | Done
Implementation | List of: pages (UI), major method/algorithms, classes
Front end (UI) created - non funtioning digital layouts
Back end created and integrated
Updated UI design
Updated requirements and test plan
Trade fair poster
Website created